PROPOSED METHODOLOGY FOR AFC

One-Month Blended AI Training, Practical Application and Post-Implementation Support

1. Approach Overview

AI Institute Africa, in partnership with Rubiem Intelligence and the University of Zimbabwe, will adopt a practical, executive-focused and impact-driven methodology designed for immediate applicability within AFC's operating environment. The updated approach is structured as a one-month blended programme that moves participants from classroom learning to online reinforcement, practical exercises and post-implementation support.

Our methodology is structured around four connected phases:

• Phase 1: Classroom training and needs alignment

• Phase 2: Online lessons and guided assignments

• Phase 3: Practical exercises using AFC-relevant scenarios

• Phase 4: Post-implementation support, reporting and adoption roadmap

2. One-Month Delivery Timeframe

| Week | Phase | Delivery Mode | Primary Outputs |
| --- | --- | --- | --- |
| Week 1 | Phase 1: Classroom | In-person, facilitator-led | Aligned agenda, AI foundations, AFC use-case priorities |
| Week 2 | Phase 2: Online Lessons | Virtual lessons and digital resources | Recorded/live sessions, guided assignments, knowledge checks |
| Week 3 | Phase 3: Practical Exercise | Hands-on practical lab | Group exercises, AI prompts, workflow prototypes, practical demonstrations |
| Week 4 | Phase 4: Support | Office hours and advisory support | Implementation Q&A, post-training report, adoption roadmap |

3. Phase 1: Classroom Training and AFC Needs Alignment

During the first week, we will engage AFC stakeholders and deliver an in-person classroom programme that establishes a common executive understanding of AI and identifies priority AFC use cases.

• Align training content with AFC strategic priorities and operational challenges

• Identify key executive roles, decision-making contexts and productivity bottlenecks

• Introduce AI, machine learning, generative AI and responsible AI governance

• Demonstrate Microsoft 365 Copilot applications for Word, Excel, PowerPoint, Outlook and Teams

• Customize examples around investment analysis, document drafting, reporting, stakeholder communication and operational efficiency

Outputs:

• Tailored AFC training agenda

• Priority AFC use-case list

• Context-specific case studies and classroom materials

4. Phase 2: Online Lessons and Guided Reinforcement

In week two, participants will complete online lessons that reinforce the classroom content and support flexible learning without disrupting executive schedules.

• Short virtual lessons covering AI productivity, prompt design and executive decision support

• Guided assignments that allow participants to apply lessons to everyday AFC work products

• Digital resources, templates and practical AI use-case guides

• Knowledge checks to confirm understanding and identify areas requiring additional coaching

Outputs:

• Online lesson completion record

• Participant assignment submissions

• Refined prompts and productivity templates

5. Phase 3: Practical Exercise and Applied Demonstrations

In week three, the programme moves from theory to application through practical exercises. Participants will work through AFC-relevant scenarios and build confidence using AI tools in a controlled environment.

• Scenario-based group exercises using AFC-relevant documents, reports and communication tasks

• Hands-on use of AI tools for summarization, analysis, drafting, presentation generation and meeting preparation

• Live facilitation to help participants improve prompts, validate outputs and manage risks

• Demonstrations of how practical AI workflows can support productivity and decision-making

Outputs:

• Completed practical exercises

• Reusable AI workflow examples

• Participant feedback on use-case feasibility

6. Phase 4: Post-Implementation Support and Sustainability

In week four, we will support implementation through advisory office hours, follow-up guidance and a concise close-out report. This ensures the programme leads to sustained adoption rather than a once-off training event.

• Post-training Q&A and advisory support sessions

• Review of participant challenges and recommended mitigations

• Guidance on governance, ethics, data protection and responsible AI adoption

• Final report summarizing insights, training outcomes and recommended next steps for AFC

Outputs:

• Post-training report

• Recommendations for AFC AI adoption

• One-page adoption roadmap and support plan

7. Training Materials and Resources

Participants will receive practical materials that can be reused after the training programme:

• Executive-level slide decks

• AI productivity and Microsoft 365 Copilot use-case guides

• Prompt templates and workflow checklists

• Reference materials and toolkits

• Certificates of completion

8. Delivery Method

• Blended delivery model: classroom, online lessons, practical exercises and post-implementation support

• Interactive facilitator-led sessions supported by digital tools and live demonstrations

• A one-month structure that allows learning, application and support to happen in a managed sequence

9. Value Addition

Our partnership brings together complementary strengths that support AFC's objectives:

• Academic rigor from the University of Zimbabwe

• Industry expertise from Rubiem Intelligence

• Specialized AI training capability from AI Institute Africa

• A practical methodology designed to create measurable adoption and immediate productivity gains