PROPOSED METHODOLOGY

Provision of Artificial Intelligence Training Services for AFC Holdings Limited

Submitted by AI Institute Africa in partnership with Rubiem Intelligence and the University of Zimbabwe

Figure 1: Four-phase methodology for AFC AI and Digital Banking Transformation training.

## 1. Approach Overview

AI Institute Africa, in partnership with Rubiem Intelligence and the University of Zimbabwe, will adopt a practical, banking-focused and impact-driven training methodology designed to ensure immediate applicability within AFC’s operational environment. The methodology supports AFC’s objective to build Artificial Intelligence capability, strengthen digital banking transformation readiness, and establish a continuous learning environment for staff across head office and branch locations.

Our methodology is structured around four implementation phases:

• Needs Alignment and Customisation

• Training Design and Delivery

• Practical Application and Demonstrations

• Evaluation and Post-Training Support

## 2. Phase 1: Needs Alignment and Customisation

Prior to training rollout, we will engage AFC stakeholders to align the programme with AFC’s strategic priorities, banking operations, staff roles and digital transformation objectives.

• Align training content with AFC’s digital transformation and AI adoption priorities.

• Identify key executive, management, technical, operational and general staff learning needs.

• Map training content to AFC’s banking processes, governance structures, operational workflows and customer service environment.

• Customise case studies for banking operations, process automation, customer service, compliance, risk management, data analytics and AI-enabled decision support.

• Review existing AFC training materials, facilities and schedules to support smooth implementation across head office and branches.

### Phase 1 Outputs

| Output | Description |
| --- | --- |
| Tailored training agenda | Programme agenda aligned to AFC priorities, roles and staff availability. |
| Banking-specific case studies | Use cases relevant to AFC operations, branch banking, compliance, customer service and digital workflows. |
| Readiness assessment inputs | Initial view of staff groups, platform needs, delivery constraints and training support requirements. |

## 3. Phase 2: Training Design and Delivery

We will deliver a structured training programme organised into role-based learning tracks. The programme will balance executive-level strategic content with practical operational examples and hands-on demonstrations for staff who require applied exposure to AI tools.

Figure 2: Role-based training tracks for AFC staff groups.

### Core Training Sessions

| Session | Focus Area | AFC Application |
| --- | --- | --- |
| Session 1 | AI Fundamentals for Banking Professionals | AI, machine learning, generative AI, agentic AI and the business value of AI in financial institutions. |
| Session 2 | AI for Productivity and Decision-Making | Report writing, document summarisation, customer communication, analysis support and executive decision support. |
| Session 3 | Microsoft 365 Copilot and AI Tool Demonstrations | Practical demonstrations in Word, Excel, PowerPoint, Outlook and Teams for banking productivity. |
| Session 4 | AI Strategy, Governance and Leadership | AI governance, responsible AI, ethics, risk, compliance and roadmap development for AFC. |
| Session 5 | Digital Transformation and Process Automation | Digital banking processes, workflow automation, robotic process automation and AI-enabled operational processes. |

## 4. Phase 3: Practical Application and Interactive Learning

To ensure maximum impact, the training will move beyond theory into practical application. Participants will work through AFC-relevant examples and guided demonstrations that show how AI can improve banking productivity, process efficiency and decision-making.

• Live demonstrations of AI tools, including Microsoft 365 Copilot and relevant generative AI applications.

• Banking-sector case studies covering customer service, risk, compliance, operations, HR, finance and executive reporting.

• Group discussions and scenario-based exercises aligned to AFC departmental responsibilities.

• AI use case development workshops to help departments identify, prioritise and document practical AI opportunities.

• Hands-on guided exercises for selected staff, including prompt engineering, data interpretation and workflow automation examples.

## 5. Blended Delivery and Digital Learning Platform

The delivery model will combine facilitator-led training, online learning, self-paced modules and interactive workshops. This approach supports participation by AFC staff across head office and branch locations while enabling continuous learning and monitoring of progress.

Figure 3: Blended training delivery and digital platform model.

• Classroom-based and facilitator-led sessions for strategic and operational engagement.

• Online and self-paced modules for flexible access by staff in different locations.

• Multi-modal content including text, video, audio, practical guides and live demonstrations.

• Multilingual support where required, including English, Shona and Ndebele learning support.

• Learning analytics, online assessments, supervisor monitoring and certificate generation.

## 6. Phase 4: Evaluation and Post-Training Support

We will measure learning effectiveness and support programme sustainability through structured evaluation and post-training reporting. The evaluation process will help AFC understand training uptake, learning outcomes and areas requiring additional support.

Figure 4: Monitoring, evaluation and continuous improvement loop.

• Participant feedback and evaluation forms.

• Knowledge checks and assessments during training sessions.

• Training progress reporting and platform analytics.

• Post-training report with key insights, attendance summaries, performance observations and recommendations for AI adoption at AFC.

• Optional follow-up advisory sessions to support implementation and internal adoption.

## 7. Training Materials and Resources

Participants will receive practical, AFC-relevant training resources that can be used during and after the programme.

• Executive-level slide decks and facilitator notes.

• Practical AI use-case guides for banking and financial services.

• Prompt engineering guides and AI productivity toolkits.

• Reference materials covering AI governance, ethics, risk and compliance.

• Digital learning resources hosted on the training platform.

• Certificates of completion and, where applicable, AI technical certification support.

## 8. Implementation Work Plan

| Phase | Key Activities | Outputs | Indicative Timing |
| --- | --- | --- | --- |
| 1. Needs Alignment | Stakeholder engagement, readiness review, staff segmentation, content alignment. | Tailored agenda, case study themes, readiness notes. | Weeks 1-2 |
| 2. Design and Preparation | Curriculum finalisation, platform setup, materials development, schedule confirmation. | Training materials, platform content, implementation schedule. | Weeks 3-6 |
| 3. Delivery and Application | Training sessions, workshops, demonstrations, AI use case development. | Trained staff, use case outputs, assessment records. | Weeks 7-20 |
| 4. Evaluation and Support | Feedback analysis, reporting, certification support, recommendations. | Progress reports, final report, post-training recommendations. | Weeks 21-24 |

## 9. Value Addition

Our partnership brings a balanced combination of academic quality assurance, industry implementation experience and specialised AI training capability.

• Academic rigor and quality assurance through the University of Zimbabwe.

• Industry expertise and digital transformation implementation insight through Rubiem Intelligence.

• Specialised AI training capability and certification support through AI Institute Africa.

• AFC-specific customisation that links AI concepts to banking operations, governance, customer service and process automation.

## 10. Expected Outcomes for AFC

| Outcome | Benefit to AFC |
| --- | --- |
| Improved AI literacy | Staff understand AI concepts, opportunities, risks and practical use cases in banking. |
| Digital transformation readiness | Teams are better prepared for process automation and digital banking workflows. |
| Departmental AI use cases | AFC receives practical AI opportunities that can inform future strategy and implementation. |
| Continuous learning capability | Staff can continue learning through digital modules, assessments and progress tracking. |
| Governance and adoption support | Leadership and management gain insight into responsible AI governance and adoption planning. |