# POST-SUMMIT RECONNAISSANCE REPORT

Date: June 29, 2026

Subject: Post-Event Analysis and Action Plan for the Two Summits

# 1. Executive Summary

The two summits successfully convened a diverse cross-section of stakeholders from government, corporate, and academic sectors. The events generated strong engagement, enhanced brand visibility, and created valuable networking opportunities.

Financially, the summits generated total combined revenue of $101,156.00, comprising $69,906.00 in direct summit revenue and $31,250.00 in partner-generated revenue. Combined expenditure amounted to $53,931.45, including $46,777.00 in summit expenses and $8,554.45 in partner expenses. This resulted in an overall net profit of $47,225.00, with partner activities contributing $22,696.00 of the total profit.

While the financial performance was strong, there remains $9,780.00 outstanding from NetOne together with an additional $5,171.50 in outstanding sponsorship and delegate payments. Outstanding vendor and speaker payments total $2,440.00 and should be settled promptly.

Operationally, the events highlighted several opportunities for improvement, particularly in integrated planning, administration, marketing execution, financial management, and post-event engagement. Addressing these issues will improve operational efficiency, strengthen stakeholder relationships, and enhance the sustainability of future summits.

# Financial Performance Dashboard

## Overall Financial Performance

| Key Performance Indicator | Amount (USD) |
| --- | --- |
| Total Revenue | 101,156.00 |
| Direct Summit Revenue | 69,906.00 |
| Partner Revenue | 31,250.00 |
| Total Costs | 53,931.45 |
| Summit Costs | 46,777.00 |
| Partner Costs | 8,554.45 |
| Overall Net Profit | 47,225.00 |
| Partner Net Profit | 22,696.00 |
| Overall Profit Margin | 46.7% |

## Outstanding Financial Position

| Item | Amount (USD) |
| --- | --- |
| Outstanding Income – NetOne | 9,780.00 |
| Other Outstanding Income | 5,171.50 |
| Total Outstanding Receivables | 14,951.50 |
| Outstanding Vendor & Speaker Payments | 2,440.00 |

## Summit Performance Snapshot

| Indicator | Status |
| --- | --- |
| Financial Performance | ✅ Strong – Net Profit of $47,225.00 |
| Stakeholder Participation | ✅ Strong representation from Government, Corporate and Academia |
| Brand Visibility | ✅ Successfully enhanced through summit participation |
| Sponsorship Performance | ✅ Strong revenue generation with outstanding collections pending |
| Operational Planning | ⚠️ Requires improved joint planning and coordination |
| Marketing Execution | ⚠️ Pre-event and post-event marketing were not fully implemented |
| Administrative Coordination | ⚠️ Resource allocation and logistics support require strengthening |
| Post-Event Engagement | ⚠️ Delegate follow-up and digital engagement require improvement |

## Executive Highlights

- Generated $101,156.00 in total revenue.

- Delivered an overall net profit of $47,225.00.

- Partner activities generated $31,250.00 in revenue and $22,696.00 in profit.

- Outstanding receivables total $14,951.50.

- Outstanding vendor obligations total $2,440.00.

- Future events require stronger joint planning, full marketing implementation, improved financial controls, balanced administrative support, and structured post-event engagement.

# 2. Summit Overview

The summits brought together representatives from government ministries, corporates, professional bodies, and higher education institutions, creating an effective platform for collaboration, innovation, and networking.

Primary expenditure categories included:

### Summit Costs

- Venue and accommodation

- Branding and merchandise

- Audio-visual production

- Event logistics

- Transportation

- Event materials

### Partner Costs

Partner-related operational expenses supporting event delivery.

### Speaker Costs

- Speaker fees

- Gifts

- Fuel allowances

# 3. Financial Summary

| Financial Metric | Amount (USD) |
| --- | --- |
| Direct Summit Revenue | 69,906.00 |
| Partner Revenue | 31,250.00 |
| Total Revenue | 101,156.00 |
| Outstanding Income – NetOne | (9,780.00) |
| Other Outstanding Income | (5,171.50) |
| Summit Costs | 46,777.00 |
| Partner Costs | 8,554.45 |
| Total Costs | 53,931.45 |
| Overall Net Profit | 47,225.00 |
| Partner Net Profit | 22,696.00 |
| Outstanding Vendor Payments | 2,440.00 |

### Financial Analysis

The summits generated an overall profit of $47,225.00 from total revenue of $101,156.00, representing an approximate 46.7% profit margin.

Partner activities made a significant contribution, generating $31,250.00 in revenue and $22,696.00 in profit after partner expenses of $8,554.45.

Outstanding receivables currently total $14,951.50, comprising $9,780.00 from NetOne and $5,171.50 from other sponsors and delegates. Recovering these funds should remain an immediate priority.

Outstanding vendor payments amount to $2,440.00 and should be settled promptly to maintain strong supplier relationships.

# 4. Organizational Observations and Key Lessons

## 4.1 Critical Logistical Issues

- Accommodation was spread across multiple venues, increasing coordination complexity.

- Planning remained reactive, resulting in unnecessary last-minute changes.

- Financial tracking lacked standardized categorization.

## 4.2 Marketing and Communications

### Pre-Event Marketing

The approved marketing campaign was not fully implemented.

Key observations include:

- Star FM campaign only ran during the final week before the summit.

- The planned ZTN television campaign was not implemented.

- The summit was not live-streamed on the day of the event.

- Marketing activities across media channels lacked coordination.

### Post-Event Marketing

Post-event marketing activities were largely not executed.

The following were either delayed or not completed:

- Event highlights

- Speaker presentations

- Summit photography

- Delegate testimonials

- Success stories

- Ongoing digital engagement

This reduced the long-term impact and visibility of the events.

## 4.3 Administration and Event Coordination

### Administrative Resource Allocation

Administrative support was unevenly distributed between the organizing partners.

- AIIA provided five team members.

- Zimpapers provided only two team members.

- Of the two Zimpapers representatives, only one was primarily responsible for logistics, placing significant operational pressure on a single individual.

### Joint Planning

Pre-summit planning was largely conducted independently rather than through an integrated planning structure.

A joint planning committee with shared ownership would improve:

- Communication

- Accountability

- Resource allocation

- Decision-making

- Event execution

## 4.4 Delegate and Financial Management

- Outstanding sponsorship payments indicate a need for stronger payment collection procedures.

- Delegate records should be better linked to organizational profiles.

- A centralized financial dashboard should be implemented for real-time financial visibility.

## 4.5 Key Lessons Learned

- Adopt integrated planning involving all organizing partners from project inception.

- Execute the approved marketing strategy in full, including radio, television, digital campaigns, and live streaming.

- Make delegate experience a core success metric.

- Centralize financial management and reporting.

- Balance administrative responsibilities across organizing partners.

- Continue structured stakeholder engagement after the summit through content, follow-up meetings, and relationship management.

# 5. Action Plan and Next Steps

| Action Item | Details | Priority |
| --- | --- | --- |
| Recover Outstanding Income | Collect the outstanding $14,951.50, including NetOne and all other outstanding payments. | Critical |
| Settle Outstanding Vendor Payments | Reconcile and pay the outstanding $2,440.00 owed to suppliers and speakers. | Critical |
| Complete Post-Event Marketing | Publish summit photographs, presentations, keynote highlights, interviews, and appreciation messages across all communication platforms. | High |
| Conduct Delegate Satisfaction Survey | Gather structured feedback from delegates on programme quality, logistics, venue, and overall experience. | High |
| Strengthen Stakeholder Engagement | Arrange follow-up meetings with strategic delegates and sponsors to build future partnerships. | High |
| Update CRM and Contact Database | Capture all delegates within the organization’s CRM and communication platforms. | Medium |
| Conduct Internal Lessons Learned Workshop | Document lessons learned and update Standard Operating Procedures (SOPs). | Medium |
| Develop a Comprehensive Marketing Plan | Ensure future campaigns include radio, television, digital media, live streaming, and structured post-event communications. | Medium |
| Establish Joint Planning Committees | Create integrated planning teams involving all organizing partners from project initiation through event delivery. | Medium |

# 6. Conclusion

The two summits successfully achieved their strategic objectives by attracting a diverse range of stakeholders, strengthening organizational visibility, and delivering an excellent financial outcome.

The events generated total combined revenue of $101,156.00, incurred combined expenditure of $53,931.45, and produced an overall net profit of $47,225.00. Partner activities contributed significantly, generating $31,250.00 in revenue and $22,696.00 in profit.

While the financial results demonstrate the commercial viability of the summit model, the review also identified opportunities to improve integrated planning, marketing execution, administration, financial controls, and post-event engagement. Addressing these areas will enable future summits to deliver even greater operational efficiency, stakeholder satisfaction, and financial performance.

With stronger collaboration between organizing partners, improved marketing implementation, disciplined financial management, and structured post-event follow-up, future editions of the summit can become the benchmark for high-impact industry events.