# POST-SUMMIT RECONNAISSANCE REPORT

Date: June 29, 2026

Subject: Post-Event Analysis and Action Plan for the Two Summits

# 1. Executive Summary

The two summits successfully convened a diverse cross-section of stakeholders from government, corporate, and academic sectors. The events generated strong engagement, enhanced brand visibility, and created valuable networking opportunities.

Financially, the summits generated total revenue of $69,906.00 against total costs of $46,777.00, resulting in a net profit of $23,129.00. While the events were profitable, there remains $9,780.00 outstanding from NetOne, together with an additional $5,171.50 in outstanding sponsorship and delegate payments from other organizations. Outstanding vendor and speaker payments amount to $2,440.00.

Operationally, the events highlighted several areas requiring improvement, particularly around integrated planning, financial controls, administration, marketing execution, and post-event engagement. Addressing these issues will improve efficiency, delegate experience, and the long-term sustainability of future summits.

# 2. Summit Overview

The summits brought together representatives from government ministries, corporate organizations, professional bodies, and academic institutions, creating a strong platform for collaboration and knowledge sharing.

Major expenditure categories included:

### Summit Costs

- Venue and accommodation

- Branding and merchandise

- Audio-visual production

- Transport and logistics

- Event materials

### Speaker Costs

- Speaker fees

- Gifts

- Fuel allowances

# 3. Financial Summary

| Financial Metric | Amount (USD) |
| --- | --- |
| Total Revenue | 69,906.00 |
| Outstanding Income – NetOne | (9,780.00) |
| Other Outstanding Income | (5,171.50) |
| Total Costs | 46,777.00 |
| Summit Costs | 38,977.00 |
| Speaker Costs | 7,800.00 |
| Net Profit | 23,129.00 |
| Outstanding Vendor Payments | 2,440.00 |

### Financial Analysis

The summits achieved an approximate 33% profit margin, demonstrating strong financial performance.

However, the organization currently has $14,951.50 in outstanding receivables that require immediate follow-up to improve cash flow. Vendor obligations totaling $2,440.00 should also be settled promptly to maintain strong supplier relationships.

# 4. Organizational Observations and Key Lessons

## 4.1 Critical Logistical Issues

### Fragmented Venue Management

Accommodation was spread across multiple venues, including Urban Lifestyles Hotel, PK Villa, Dreamwoods, and Flamboyant. This increased coordination complexity, created unnecessary transport challenges, and reduced operational efficiency.

### Reactive Planning

Planning remained largely reactive throughout the preparation period, leading to numerous last-minute adjustments and increased pressure on the organizing team.

### Inconsistent Cost Tracking

Financial records lacked standardized categorization, making expenditure tracking and reporting more difficult than necessary.

## 4.2 Marketing and Communications

### Incomplete Pre-Event Marketing Campaign

The planned marketing campaign was not fully implemented.

Key observations include:

- Star FM radio promotion only ran during the final week before the summit, limiting audience reach.

- The planned ZTN television campaign was not implemented.

- The summit was not live-streamed on the event day, reducing engagement with stakeholders who could not attend physically.

- Promotional activities were not coordinated sufficiently across all available media channels.

### Limited Post-Event Marketing

Post-event marketing activities were not carried out as planned.

There was limited publication of:

- Event highlights

- Speaker presentations

- Summit photographs

- Delegate testimonials

- Success stories

- Follow-up engagement content

This reduced opportunities to maximize the long-term value and visibility of the summits.

## 4.3 Administration and Event Coordination

### Imbalanced Administrative Resources

The administrative structure was not adequately balanced between the organizing partners.

Administration consisted of:

- Five AIIA team members

- Two Zimpapers team members

Of the two Zimpapers personnel, only one individual was responsible for the majority of logistics coordination, creating an uneven workload and reducing operational effectiveness.

### Isolated Pre-Summit Planning

Planning activities before the summit were largely conducted independently rather than jointly between the organizing partners.

Greater collaboration during planning would have:

- Improved communication

- Reduced duplication of work

- Increased accountability

- Enabled faster decision-making

- Produced a more coordinated event delivery.

## 4.4 Delegate and Financial Management

### Weak Payment Collection

Outstanding sponsorship and delegate income indicates that payment collection procedures require strengthening.

Clear payment milestones, earlier invoicing, and structured follow-up should become standard practice.

### Delegate Information Management

Delegate information was not consistently linked to organizations, limiting opportunities for structured relationship management after the summit.

### Limited Real-Time Financial Visibility

Financial reporting relied on multiple spreadsheets rather than a centralized financial dashboard, reducing visibility throughout the planning process.

## 4.5 Key Lessons Learned

- Integrated Planning is Essential

Future summits should be jointly planned from inception by all organizing partners, with clear responsibilities and shared decision-making.

- Marketing Must Be Fully Executed

Approved marketing plans should be implemented in full across radio, television, digital platforms, social media, and live streaming to maximize attendance and brand exposure.

- Delegate Experience Should Remain a Core KPI

Delegate satisfaction should continue to influence venue selection, accommodation, catering, logistics, and communication.

- Dedicated Financial Management

A centralized financial management process should provide real-time visibility of income, expenditure, receivables, and outstanding obligations.

- Balanced Administrative Resources

Administrative responsibilities should be distributed equitably across all organizing partners to improve coordination and reduce operational pressure on individual staff members.

- Post-Event Engagement is Critical

The summit should not end when delegates leave. Structured post-event communication, media coverage, stakeholder follow-up, and digital content should continue for several weeks after the event.

# 5. Action Plan and Next Steps

| Action Item | Details | Priority |
| --- | --- | --- |
| 1. Recover Outstanding Income | Collect the outstanding $14,951.50, including NetOne and all other outstanding payments. | Critical |
| 2. Settle Outstanding Vendor Payments | Reconcile and pay the outstanding $2,440.00 owed to suppliers and speakers. | Critical |
| 3. Complete Post-Event Marketing | Publish summit photographs, presentations, keynote highlights, interviews, and appreciation messages across all communication platforms. | High |
| 4. Conduct Delegate Satisfaction Survey | Obtain structured feedback from delegates regarding programme quality, logistics, venue, and overall experience. | High |
| 5. Strengthen Stakeholder Engagement | Arrange follow-up meetings with strategic delegates and sponsors to build future partnerships and sponsorship opportunities. | High |
| 6. Update CRM and Contact Database | Capture all delegates within the organization’s CRM and communication platforms for continuous engagement. | Medium |
| 7. Conduct Internal Lessons Learned Workshop | Review the summit, document lessons learned, and update Standard Operating Procedures (SOPs). | Medium |
| 8. Develop a Comprehensive Marketing Plan | Ensure future campaigns include radio, television, digital media, live streaming, and coordinated post-event communications. | Medium |
| 9. Establish Joint Planning Committees | Create integrated planning teams involving all organizing partners from project initiation through event delivery. | Medium |

# 6. Conclusion

The two summits achieved their strategic objectives by attracting a diverse range of stakeholders, strengthening organizational visibility, and delivering a positive financial outcome.

With total revenue of $69,906.00, total expenditure of $46,777.00, and a net profit of $23,129.00, the events demonstrated strong commercial viability.

However, the review identified opportunities for improvement in financial management, joint planning, administration, logistics, marketing execution, and post-event engagement. The incomplete implementation of the pre-event marketing campaign, limited post-event communications, uneven allocation of administrative resources, and isolated planning processes reduced the overall impact that could have been achieved.

Implementing the recommendations outlined in this report will strengthen future summit delivery, improve stakeholder satisfaction, enhance operational efficiency, and position future events for even greater strategic and financial success.