| dates |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (2 months’ duration) | Training readiness assessment | Physical (1) | Online | Physical (2) | Assesment Test (Online) |
| Exco | 1st July | 6th July | 24th July | 3rd Aug | 11th Aug |
| Managment | 2nd July | 8th July | 17th July | 6th Aug | 11th Aug |
| Support Functions (HR, Risk, Audit) | 7th July | 15th July | 22nd July | 10th Aug | 11th Aug |
| Branches (Southern) | 9th July | 20th July | 30th July | 17th Aug | 25th Aug |
| Branches (Northern) | 10th July | 23rd July | 31st July | 19th Aug | 25th Aug |
| Technical | 13th July | 27th July | 5th Aug | 24th Aug | 28th Aug |