## Plan
ID | Task | Owner | Start | End | Duration (days) | Dependencies
S0 | Project kickoff: repo conventions, branching strategy, code review rules, definition-of-done, weekly demo cadence | Shared | 2026-02-18 | 2026-02-19 | 2
S0.1 | AI-agent prompt library + codegen templates (API stubs, DB migrations, UI pages) + coding standards | Shared | 2026-02-18 | 2026-02-22 | 5 | S0
S0.2 | CI/CD baseline: linting, unit test runner, build pipeline, env config templates (.env.example), container skeleton | Shared | 2026-02-20 | 2026-02-26 | 7 | S0
W1 | Freeze MVP scope + success criteria + 10-step demonstration scenario (evidence→dataset loop) | Wills | 2026-02-18 | 2026-02-20 | 3 | S0
W2 | ICD v1.0: endpoints + request/response contracts (upload, evidence, extraction, validation, CDM, publishing, audit) | Wills | 2026-02-18 | 2026-02-25 | 8 | W1
W3 | CDM v1.0: entities (Person, Organization, Document, Transaction; Asset optional) + schema versioning rules | Wills | 2026-02-18 | 2026-02-26 | 9 | W1
W4 | Governance baseline spec: RBAC roles + permissions + audit event catalog (ingest/validate/merge/publish) | Wills | 2026-02-26 | 2026-03-03 | 6 | W2
W5 | Trust scoring design: weights, thresholds, and validation-trigger logic (configurable) | Wills | 2026-03-01 | 2026-03-05 | 5 | W2
W6 | Entity resolution policy: matching rules + golden record merge policy + merge history requirements | Wills | 2026-03-10 | 2026-03-16 | 7 | W3
W7 | Dataset card spec: required fields (schema version, lineage, timestamps, approval status) + template | Wills | 2026-03-15 | 2026-03-20 | 6 | W3
W8 | Integration verification pack: E2E tests (traceability, governance enforcement, reproducibility) + RTM-lite | Wills | 2026-03-20 | 2026-03-30 | 11 | W2,W3,W4
W9 | Final acceptance + stakeholder demo script + release sign-off package | Wills | 2026-04-07 | 2026-04-11 | 5 | S4
T1 | Backend scaffold: API gateway + service skeletons (ingestion, evidence, intelligence, validation, publishing, governance) | TK | 2026-02-18 | 2026-02-25 | 8 | W2,S0.2
T2 | DB schema v1: tenants/users/roles, evidence_objects, documents, extraction_results, validation_tasks, datasets, audit_events | TK | 2026-02-20 | 2026-02-28 | 9 | T1,W3
T3 | Evidence intake API: upload scanned PDFs + SHA-256 hashing + metadata persistence + idempotency key | TK | 2026-02-24 | 2026-03-03 | 8 | T2
T4 | Immutable evidence storage: content-addressed paths + lock flag + evidence retrieval API + checksum verify | TK | 2026-02-28 | 2026-03-08 | 9 | T3
T5 | Async job framework: queue + workers + retries/backoff + job state tracking (ingest→ocr→extract→validate) | TK | 2026-03-01 | 2026-03-12 | 12 | T1
T6 | OCR pipeline: run OCR job + store text blocks + page references + confidence aggregates | TK | 2026-03-05 | 2026-03-15 | 11 | T5,T4
T7 | Extraction engine: configurable fields + confidence scoring + evidence pointers (page + region/bbox) | TK | 2026-03-10 | 2026-03-22 | 13 | T6,W2
T8 | Trust scoring implementation + validation task generator (below threshold) + thresholds config | TK | 2026-03-18 | 2026-03-28 | 11 | T7,W5
T9 | Validation backend: approve/reject endpoints + validation history + field-level audit trail | TK | 2026-03-20 | 2026-03-31 | 12 | T8,W4
T10 | CDM mapper: map validated fields into CDM v1.0 + schema version persistence + lineage links to evidence | TK | 2026-03-25 | 2026-04-03 | 10 | T9,W3
T11 | Entity resolution basic: exact match + simple fuzzy match + golden record creation + merge history store | TK | 2026-03-29 | 2026-04-07 | 10 | T10,W6
T12 | Dataset publishing: build dataset from CDM + dataset versioning + CSV/JSON export | TK | 2026-03-28 | 2026-04-08 | 12 | T10
T13 | Dataset card generator: populate required metadata + lineage embedding + approval status | TK | 2026-03-30 | 2026-04-08 | 10 | T12,W7
T14 | Governance backend: RBAC enforcement middleware + audit logging for ingest/validate/merge/publish + download access checks | TK | 2026-03-25 | 2026-04-09 | 16 | W4,T1
A1 | Frontend scaffold: app shell + auth wiring + role-based navigation (Operator/Validator/Compliance/Admin) | Arthur | 2026-02-18 | 2026-02-26 | 9 | W2,S0.2
A2 | Upload UI: evidence upload + metadata capture + job status dashboard (ingest/ocr/extract) | Arthur | 2026-02-24 | 2026-03-06 | 11 | A1,T3
A3 | Evidence viewer: PDF preview + page navigation + show OCR text blocks + highlight evidence pointers (bbox/region) | Arthur | 2026-03-01 | 2026-03-15 | 15 | A1,T4,T6
A4 | Validation queue UI: task list + field-level approve/reject + comments + validation history panel | Arthur | 2026-03-12 | 2026-03-31 | 20 | A3,T9
A5 | Golden record review UI: view match candidates + confirm merges + merge history display | Arthur | 2026-03-22 | 2026-04-06 | 16 | A4,T11
A6 | Dataset portal UI: dataset list + versions + dataset card view + download controls (RBAC) | Arthur | 2026-03-25 | 2026-04-09 | 16 | A4,T12,T13
A7 | Audit log viewer UI: read-only log table + filters (actor/action/date/object) + export CSV (optional) | Arthur | 2026-03-30 | 2026-04-10 | 12 | A1,T14
S1 | Weekly integration demo #1 (Sprint 1): upload→hash/lock→retrieve evidence | Shared | 2026-03-03 | 2026-03-03 | 1 | T3,T4,A2
S2 | Weekly integration demo #2 (Sprint 2): OCR+extraction outputs with evidence pointers | Shared | 2026-03-17 | 2026-03-17 | 1 | T6,T7,A3
S3 | Weekly integration demo #3 (Sprint 3): validation workflow end-to-end (approve/reject) + audit events | Shared | 2026-03-31 | 2026-03-31 | 1 | T9,A4,T14
S3.1 | E2E Working Loop (Build #1): upload→OCR/extract→validate→CDM→publish dataset (CSV+card) with traceability | Shared | 2026-04-01 | 2026-04-04 | 4 | T10,T12,T13,A6
S4 | Hardening & scale-ready pass: retries/idempotency, performance smoke tests, observability, security checks | Shared | 2026-04-04 | 2026-04-07 | 4 | S3.1
S5 | Final demo rehearsal + bug bash + documentation handover (runbook, install guide, known limits) | Shared | 2026-04-08 | 2026-04-10 | 3 | S4
M0 | Milestone: Sprint 0 complete (collaboration + CI/CD + AI-agent templates ready) | Milestone | 2026-02-26 | 2026-02-26 | 1 | S0.1,S0.2
M1 | Milestone: MVP scope + ICD/CDM baseline approved | Milestone | 2026-02-26 | 2026-02-26 | 1 | W1,W2,W3
M2 | Milestone: Evidence intake working (upload + hash + lock + retrieve + metadata) | Milestone | 2026-03-08 | 2026-03-08 | 1 | T4,A2
M3 | Milestone: OCR+Extraction produces fields w/ confidence + evidence pointers | Milestone | 2026-03-22 | 2026-03-22 | 1 | T7,A3
M4 | Milestone: Trust scoring + validation tasks working | Milestone | 2026-03-28 | 2026-03-28 | 1 | T8
M5 | Milestone: Validation workflow complete (UI + backend + audit logging) | Milestone | 2026-03-31 | 2026-03-31 | 1 | T9,A4,T14
M6 | Milestone: CDM mapping complete with lineage | Milestone | 2026-04-03 | 2026-04-03 | 1 | T10
M7 | Milestone: Entity resolution + golden records available | Milestone | 2026-04-07 | 2026-04-07 | 1 | T11,A5
M8 | Milestone: Dataset publishing + dataset card + downloads working | Milestone | 2026-04-09 | 2026-04-09 | 1 | T12,T13,A6
M9 | Milestone: MVP complete (demo-ready) – end-to-end with governance + traceability | Milestone | 2026-04-11 | 2026-04-11 | 1 | W9,S5

## Gantt
ID | Task | Owner | W1 18 Feb–24 Feb | W2 25 Feb–03 Mar | W3 04 Mar–10 Mar | W4 11 Mar–17 Mar | W5 18 Mar–24 Mar | W6 25 Mar–31 Mar | W7 01 Apr–07 Apr | W8 08 Apr–11 Apr
S0 | Project kickoff: repo conventions, branching strategy, code review rules, definition-of-done, weekly demo cadence | Shared
S0.1 | AI-agent prompt library + codegen templates (API stubs, DB migrations, UI pages) + coding standards | Shared
S0.2 | CI/CD baseline: linting, unit test runner, build pipeline, env config templates (.env.example), container skeleton | Shared
W1 | Freeze MVP scope + success criteria + 10-step demonstration scenario (evidence→dataset loop) | Wills
W2 | ICD v1.0: endpoints + request/response contracts (upload, evidence, extraction, validation, CDM, publishing, audit) | Wills
W3 | CDM v1.0: entities (Person, Organization, Document, Transaction; Asset optional) + schema versioning rules | Wills
W4 | Governance baseline spec: RBAC roles + permissions + audit event catalog (ingest/validate/merge/publish) | Wills
W5 | Trust scoring design: weights, thresholds, and validation-trigger logic (configurable) | Wills
W6 | Entity resolution policy: matching rules + golden record merge policy + merge history requirements | Wills
W7 | Dataset card spec: required fields (schema version, lineage, timestamps, approval status) + template | Wills
W8 | Integration verification pack: E2E tests (traceability, governance enforcement, reproducibility) + RTM-lite | Wills
W9 | Final acceptance + stakeholder demo script + release sign-off package | Wills
T1 | Backend scaffold: API gateway + service skeletons (ingestion, evidence, intelligence, validation, publishing, governance) | TK
T2 | DB schema v1: tenants/users/roles, evidence_objects, documents, extraction_results, validation_tasks, datasets, audit_events | TK
T3 | Evidence intake API: upload scanned PDFs + SHA-256 hashing + metadata persistence + idempotency key | TK
T4 | Immutable evidence storage: content-addressed paths + lock flag + evidence retrieval API + checksum verify | TK
T5 | Async job framework: queue + workers + retries/backoff + job state tracking (ingest→ocr→extract→validate) | TK
T6 | OCR pipeline: run OCR job + store text blocks + page references + confidence aggregates | TK
T7 | Extraction engine: configurable fields + confidence scoring + evidence pointers (page + region/bbox) | TK
T8 | Trust scoring implementation + validation task generator (below threshold) + thresholds config | TK
T9 | Validation backend: approve/reject endpoints + validation history + field-level audit trail | TK
T10 | CDM mapper: map validated fields into CDM v1.0 + schema version persistence + lineage links to evidence | TK
T11 | Entity resolution basic: exact match + simple fuzzy match + golden record creation + merge history store | TK
T12 | Dataset publishing: build dataset from CDM + dataset versioning + CSV/JSON export | TK
T13 | Dataset card generator: populate required metadata + lineage embedding + approval status | TK
T14 | Governance backend: RBAC enforcement middleware + audit logging for ingest/validate/merge/publish + download access checks | TK
A1 | Frontend scaffold: app shell + auth wiring + role-based navigation (Operator/Validator/Compliance/Admin) | Arthur
A2 | Upload UI: evidence upload + metadata capture + job status dashboard (ingest/ocr/extract) | Arthur
A3 | Evidence viewer: PDF preview + page navigation + show OCR text blocks + highlight evidence pointers (bbox/region) | Arthur
A4 | Validation queue UI: task list + field-level approve/reject + comments + validation history panel | Arthur
A5 | Golden record review UI: view match candidates + confirm merges + merge history display | Arthur
A6 | Dataset portal UI: dataset list + versions + dataset card view + download controls (RBAC) | Arthur
A7 | Audit log viewer UI: read-only log table + filters (actor/action/date/object) + export CSV (optional) | Arthur
S1 | Weekly integration demo #1 (Sprint 1): upload→hash/lock→retrieve evidence | Shared
S2 | Weekly integration demo #2 (Sprint 2): OCR+extraction outputs with evidence pointers | Shared
S3 | Weekly integration demo #3 (Sprint 3): validation workflow end-to-end (approve/reject) + audit events | Shared
S3.1 | E2E Working Loop (Build #1): upload→OCR/extract→validate→CDM→publish dataset (CSV+card) with traceability | Shared
S4 | Hardening & scale-ready pass: retries/idempotency, performance smoke tests, observability, security checks | Shared
S5 | Final demo rehearsal + bug bash + documentation handover (runbook, install guide, known limits) | Shared
M0 | Milestone: Sprint 0 complete (collaboration + CI/CD + AI-agent templates ready) | Milestone
M1 | Milestone: MVP scope + ICD/CDM baseline approved | Milestone
M2 | Milestone: Evidence intake working (upload + hash + lock + retrieve + metadata) | Milestone
M3 | Milestone: OCR+Extraction produces fields w/ confidence + evidence pointers | Milestone
M4 | Milestone: Trust scoring + validation tasks working | Milestone
M5 | Milestone: Validation workflow complete (UI + backend + audit logging) | Milestone
M6 | Milestone: CDM mapping complete with lineage | Milestone
M7 | Milestone: Entity resolution + golden records available | Milestone
M8 | Milestone: Dataset publishing + dataset card + downloads working | Milestone
M9 | Milestone: MVP complete (demo-ready) – end-to-end with governance + traceability | Milestone
Legend
Wills | Architecture/Integration
TK | Pipeline/Data Services
Arthur | Workflow/UX
Shared | Collaboration/Integration/Hardening
Milestone | Milestones