## Sheet1
Project | Initiatives | BRD | Due Date | Detailed Technical Design | Business Lead | Team Members | Technical Lead | Team Members | RFP OUT | Completion Date | Capex Savings | Revenue 100% Certain | Opex Savings | Capex Budget | Project Duration
#1 Projct - Service Experience Centre | Branch Transformation | Yes | [9 empty] | 100000 |  |  |  | 42k/Branch
| Returns, Reports and Registers | Yes | 2026-12-03 | 16/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/04/26 |  | 35000
#2 Projct - Virtual Experience Centre | Virtual Service Centre | Yes | 2026-12-03 | 20/03/26 | [7 empty] | 150000
| Implement a Digital Branch (Branches) | Yes | 2026-10-03 | 13/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/05/26
#3 Projct - Digital Experience Centre | Implement a Digital Branch (ZITF) | Yes | 2026-10-03 | 13/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 13/04/26 |  |  | 108000
#4 Projct - Omni-Channel | Internet Banking | Yes | 2026-12-03 | 16/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 30/03/26 |  | 50000
| Omni-channel (AFC Group Onboarding) | Yes | 13/03/2026 | 18/03/26 |  |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald | 31/03/26 | 30/06/26 | [5 empty] | See HR Savings
#5 Projct - CCD Transformation | CCD/ CIT Optimisation | Yes | 18/03/2026 | 27/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, | Mugari |  |  | 28/08/26 |  |  | 15000 |  |  | To get competitive prices from more CIT companies and expect a saving of 1000 per month. Invoice validation and insurance limits adjustements will assist in the saving
#6 Projct - Telecoms & Internet | Telecoms HQ + Branch + HQ | Yes | 13/03/2026 | 20/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, | Mugari |  | 31/03/26 | 30/06/26 |  |  | 150315
| FCT (Branch Mobile Communications) | Yes | 2026-07-03 | 2026-08-03 | Choruwa | Choruwa | Choruwa |  |  | 13/03/26 |  |  | 23647
| Internet Bandwidth | Yes | 2026-11-03 | 13/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 20/03/26 |  |  | 561370
| eMails | Yes | 2026-12-03 | 19/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, |  |  | 31/03/26 | 15/05/26 |  |  | 40865
| Bulk SMS (Alerts and Marketing) | Yes | 2026-12-03 | 19/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald | 31/03/26 | 15/05/26 |  |  | 80000
#7 Projct - Back-Office Digitalisation | Fuel Card | Yes | 13/03/2026 | 19/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, |  |  | 30/03/26 | 30/04/26 |  |  | 95261
| Stationary | Yes | 13/03/2026 | 19/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 30/04/26 |  |  | 39686
| Stores- Stock Management | Yes | 17/03/2026 | 20/03/26 | Nhamburo |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/07/26
| Document Collection & Management | Yes | 17/03/2026 | 20/03/26 | Nhamburo |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/07/26 |  |  | 20000
| Overtime | Yes | 20/4/2026 | 27/04/26 | Hr |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/06/26 |  |  | 35000
| Branch Initiated Expenses , Requisitions | Yes | 2026-12-03 | 16/03/26 | Mugari |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/04/26
Yes
#7 Projct - Security Guards Project | Security Guards | Yes | 13/03/2026 | 13/03/26 | Mugari | Choruwa, Josiah, Lloyd, Donald, |  |  | 31/03/26 | 30/06/26 |  |  | 158052
#8 Projct - Autoreconciliations | Suspense Accounts and Reconcilliations | Yes | 2026-12-03 | 16/03/26 | Lloyd |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 15/04/26 |  | 123546
Yes
#9 Projct - POS Operating model | POS SIM CARDS | Yes | 2026-11-03 | 18/03/26 | Tatenda Tsikira |  | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 25/03/26 |  |  | 185693
| POS Analyis | Yes | 19/03/2026 | 31/03/26 | Mugari | lloyd,Josiah, Archie, Patie, Arthur | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 30/05/26
#10 Projct - Fleet Management | Fleet Management | Yes | 23/03/2026 | 27/03/26 | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 30/05/26 |  |  | 11963 |  |  | project to save 10% of the maintanance costs
#11 Projct - Asset Managment System | Asset Management / Asset Tagging | Yes | 13/04/2026 | 17/04/26 | Mugari | Archie, Eddie, Nyasha, Tanaka, Donald | Tatenda Tsikira | Archie, Eddie, Nyasha, Tanaka, Donald |  | 30/05/26
| Assests disposal | Yes | 13/03/2026 | 31/03/26 | Mugari |  |  |  |  | 15/04/26
#12 Projct - Mobile Phone & laptop Policy | Phones and Laptops | Yes | 25/03/2026 | 25/03/26 | Mugari |  |  |  |  | 15/05/26
#13 Projct - Computers | Computers | Yes | 25/03/2026 | 25/03/26 | Mugari |  |  |  |  | 15/05/26 | 20000
#14 Projct - Utilities costs | Utilities Expenses | Yes | 2026-02-04 | 16/04/26 | Mugari |  |  |  | 23/04/26 | 2026-01-06
#15 Projct - Estate Operating model | Estate Management | Yes | 2026-02-04 | 16/04/26 | Mugari |  |  |  | 23/04/26 | 2026-01-06
#16 Projct - Data Protection | Stores- HR Files and Tittle Deeds | Yes | 17/03/2026 | 20/03/26 | Mugari | Archie, Eddie, Nyasha, Tanaka, Donald | Tatenda Tsikira |  |  | 15/07/26
#17 Projct - Registry Protection | Registry - Fire protection | Yes | 15/04/2026 |  | Mugari |  |  |  |  | 30/05/26
#18 Projct - eArchiving / Digitalisation | Registry | yes | 17/03/2026 | 20/03/26 | Mugari | Archie, Eddie, Nyasha, Tanaka, Donald | Tatenda Tsikira |  |  | 15/07/26
#19 Projct - Digital HR | HR - Recruitment | Yes | 28/04/2026 | 2026-07-05 | Tatenda Tsikira |  | Tatenda Tsikira |  |  | 30/06/26
| HR-Performance Management | Yes | 2026-12-03 | 19/03/26 | Tatenda Tsikira |  | Tatenda Tsikira |  |  | 15/04/26
| Staff Exit Closure | Yes | 28/04/2026 | 2026-07-05 | Tatenda Tsikira |  | Tatenda Tsikira |  |  | 30/06/26
#20 Projct - Digital Training | Training - AI and Digital | Yes | 20/03/2026 | 20/03/26 | Tatenda Tsikira |  | Tatenda Tsikira |  | 31/03/26 | 29/05/26 |  |  | 150000
#21 Projct - Agents Business | Agent Banking Model | yes | 22/04/2026 |  | Mugari |  |  |  |  | 21/09/26 |  | 7000
#22 Projct - Agents Business | Agent Commission | Yes | 27/04/2026 | 2026-06-05 | Tatenda Tsikira |  |  |  |  | 15/06/26
#23 Projct - Schools business | Schools (To increase deposits) - to be phased | yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  |  |  |  | 200000
#23 Projct - Civil Servants & Pensions | Civil Servants & Pensions | yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira
#23 Projct - Agriculture | Agriculture | Yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira
#24 Proct - Microfinance business | Microfinance | Yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  |  |  |  | 3013800 |  |  |  | Increase loan book by 3.7 M to 12 M
#25 Projct - Cards Business | VISA Analysis | Yes | 2025-06-03 | 2025-08-03 | Mugari |  | Tatenda Tsikira |  |  | 13/03/26 |  |  | 36000
#26 Projct - ATM Revenue Maximisation | ATM Analysis | Yes | 27/04/2026 | 2026-11-05 | Tatenda Bandama |  | Tatenda Tsikira |  |  | 15/08/26 |  | 17900
#27 Projct - MTA Business | MTA Analysis | Yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  |  |  |  | 78000
#28 Projct - Intelligent Pricing | Pricing Hand Book | yes | 18/03/2026 | 23/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  | 31/03/26 | 30/05/26 |  | 1300000
#29 Projct - Private banking | Private Banking | Yes | 2026-06-03 | 18/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  |  |  |  | 55000
| Safe Custody | Yes | [9 empty] | 10000
#30 Projct - Revenue Assurance | Revenue Assurance |  | 18/03/2026 | 23/03/26 | Tatenda Bandama |  | Tatenda Tsikira |  | 31/03/26 | 30/05/26 |  | 100000
#31 Projct - Insurance | Insurance |  | 2026-06-03 | 13/03/26 | Mugari |  | Tatenda Tsikira
#32 Projct - Intelligent Automation | Flexidoc Upgrade | Yes
#33 Projct - Product & Experience Innovation | Innovation and Product Management | Yes | 2026-04-04 | 2026-04-05 | [7 empty] | 990000
#34 Projct - ICT Cost optimisation | ICT Tenders |  | 2026-06-03 | 13/03/26 | Tatenda Tsikira |  |  |  |  | 18/05/26 |  |  | 110000
#35 Projct - Technical Operations | ICT Processes | Yes | 18/5/2026 |  | Tatenda Tsikira |  |  |  |  | 15/09/26
#36 Projct - Technical Operations | DT Processes | Yes | 18/5/2026 |  | Tatenda Tsikira |  |  |  |  | 15/09/26
#37 Projct - Gen Z | Account opening (50 K Net Increase ) |  | 2026-06-03 | 23/03/26 | Tatenda Bandama
#38 Biller Integration | Billers | Yes
#39 Projct - Supply Chain Digitalisation | Procument | Yes | 2026-02-04 | 17/04/26 | Kudzi |  |  |  |  | 17/08/26
| Contract Management | Yes | 2026-02-04 | 17/04/26 | Kudzi |  |  |  |  | 17/08/26
| Travel, Hotel and Transport | yes | 2026-02-04 | 17/04/26 | Kudzi |  |  |  |  | 17/08/26 |  |  | 17592
#40 Projct - Loan Account | Loan Account | [10 empty] | 358636.8
#41 Projct - Service Provider Payments | Service Provider Payments |  | 15/03/2026 | 31/03/26 | [7 empty] | 35000 | 190000
#42 Projct - IDC And Data Cleanup | IDC Cleanup and BI | Yes
#43 Projct - Infrastructure Sharing | Infastructure Sharing | Yes
[11 empty] | 0 | 0 | 17592 | 0
Total | [10 empty] | 20000 | 6623882.8 | 2046036 | 0
[13 empty] | 8669918.8 |  | 8669918.8

## Sheet1 (2)
PROCESSES | # | Project Name | Initiative | Efficiency Gain | Compliance/Risk | Capex Savings | Revenue 100% Certain | Revenue 60% Certain | Opex Savings | Project Budget | Project Duration
| 1 |  | Corporate Strategy
| 2 |  | Digital Transformation Strategy
| 3 |  | AI Strategy and Roadmap
| 4 |  | Business Model
| 5 |  | Operating Model
| 6 |  | Process Architecture
| 7 |  | Heatmap
| 8 |  | Digital Maturity
| 9 |  | Process Model
| 10 |  | Enterprise Architecture |  |  | 300000
| 11 |  | Budgeting
| 12 |  | Branch Profit/ Traffic Analyis |  |  | 200000
| 13 |  | Opex Analysis
| 14 |  | Capex Analysis |  |  | 200000
| 15 |  | Revenue Analyis
| 16 |  | Implementation Plan
|  | Project | Initiatives | Efficiency Gain | Compliance/Risk | Capex Savings | Revenue 100% Certain | Revenue 60% Certain | Opex Savings | Capex Budget | Project Duration
| 34 | #11 Projct - Estate Operating model | Estate Management
| 35 | #12 Projct - Data Protection | Stores- HR Files and Tittle Deeds | Yes
| 36 | #13 Projct - Registry Protection | Registry - Fire protection |  | yes
| 31 | #14 Projct - eArchiving / Digitalisation | Registry
| 37 | #15 Projct - Digital HR | HR - Recruitment | Yes | Yes
| 38 |  | HR-Performance Management | Yes
| 39 |  | HR - Police Clearance |  | Yes
| 40 | #16 Projct - Digital Training | Training - AI and Digital | [5 empty] | 150000
| 50 | #17 Projct - Agents Business | Agent Banking |  |  |  |  | 7000
| 51 | #17 Projct - Agents Business | Agent Commission | Yes
| 53 | #18 Projct - Schools business | Schools (To increase deposits) |  |  |  |  | 200000
| 54 | #19 Proct - Microfinance business | Microfinance |  |  |  | 2263800 | 750000 |  |  |  | Increase loan book by 3.7 M to 12 M
| 56 | #20 Projct - Cards Business | VISA Analysis | [5 empty] | 36000
| 57 | #21 Projct - ATM Revenue Maximisation | ATM Analysis |  |  |  | 17900
| 58 | #22 Projct - MTA Business | MTA Analysis
| 59 | #23 Projct - Intelligent Pricing | Pricing Hand Book |  |  |  | 1300000
| 60 | #25 Projct - Private banking | Private Banking | Yes |  |  |  | 10000
| 64 | #26 Projct - Revenue Assurance | Revenue Assurance |  |  |  |  | 100000
| 65 | #27 Projct - Insurance | Insurance
| 70 | #28 Projct - Intelligent Automation | Flexidoc Upgrade | Yes
| 70 | #29 Projct - Product & Experience Innovation | Innovation and Product Management |  |  |  | 990000
| 77 | #30 Projct - ICT Cost optimisation | ICT Tenders | [5 empty] | 110000
| 78 | #31 Projct - Technical Operations | ICT Processes | Yes
| 79 | #31 Projct - Technical Operations | DT Processes | Yes
| 62 | #33 Projct - Gen Z | Account opening (50 K Net Increase )
| 61 | #34 Biller Integration | Billers | Yes
| 80 | #32 Projct - Supply Chain Digitalisation | Procument | Yes
| 81 |  | Contract Management | Yes
| 82 |  | Travel, Hotel and Transport | [5 empty] | 17592
[6 empty] | 0 | 0 | 0 | 17592 | 0
|  | Total |  |  |  | 0 | 4571700 | 1067000 | 331184 | 0
[8 empty] | 5638700 | 331184
| 83 | #33 Org Design | Organisation Headcount
| 84 | #33 Org Design | Restructure
| 85 | #33 Org Design | New Departments and Roles
|  | Project Name | Initiative | Efficiency Gain |  | Capex Savings |  | Revenue Increase | Opex Savings | Project Budget
|  |  | HR Total | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | Project Name | Initiative | Efficiency Gain |  | Capex Savings |  | Revenue Increase | Opex Savings | Project Budget
|  |  | Grand Total | #REF! |  | #REF! |  | #REF! | #REF! | #REF!
Infrastructure Sharing
| 86 |  | ATM
| 87 |  | Branch
| 88 |  | Internet bandwidth
| 89 |  | Internet connectivity
| 90 |  | Fuel
| 91 |  | Hardware
| 92 |  | VSC
| 93 |  | Flexiexpress
| 94 |  | AI