## Financials
| Aiia | Target | Realised | Net | January Target |  |  |  | March Target
1 | Zimpapers Summit - Vic Falls | 190800 | 45% | 85860 | Complete Concept | Publish adverts | Get Speakers |  | Complete Program | Publish adverts | Get Speakers
2 | Zimpapers Summit - Trout Beck | 16000 | 40% | 6400 | Complete Concept | Publish adverts | Get Speakers |  | Complete Program | Publish adverts | Get Speakers
3 | Zimpapers Summit - Harare | 37500 | 40% | 15000 | Complete Concept | Publish adverts | Get Speakers |  | Complete Program | Publish adverts | Get Speakers
4 | Diploma Training | 55000 | 90% | 49500 | Hexco Registration | Publish adverts | Create content | Course Acredited | Hexco Registration | Publish adverts | Create content | Course Acredited
5 | Certficate Training | 56000 | 90% | 50400 | Hexco Registration | Publish adverts | Create content | Course Acredited | Hexco Registration | Publish adverts | Create content | Course Acredited
6 | Technical Certification | 27500 | 90% | 24750 | Hexco Registration | Publish adverts | Create content | Course Acredited | Hexco Registration | Publish adverts | Create content | Course Acredited
6 | IoBZ Training | 90000 | 50% | 45000 | Client Meeting | Sign agreement | Create content |  | Approach client | Sign agreement
7 | AFC Training | 50000 | 90% | 45000 | Win Tender | Secure stakeholder 1 | Secure stakeholder 2 |  | Write RFP | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
8 | Short-Courses | 20000 | 70% | 14000 | Win 1 Client | Publish adverts | Submit 2 proposals |  | Win 1 Client | Publish adverts | Submit 2 proposals
9 | POTRAZ / Funded AI Solutions | 35000 | 65% | 22750 | Exchange propsoal |  |  |  | Exchange propsoal
10 | Fintech / Pricing system | 24000 | 100% | 24000 | Complete platform |  |  |  | Complete platform
11 | eLearning Platform | 20000 | 100% | 20000 | complere phase 1 | develop brochure | develop roadmap | secure compute | acquire 2 corporates | Launch for Aiia | get 100 Users | testing
|  | 621800 |  | 402660
rubiem
1 | RA 1 | 95200 | 80% | 76160 | Sign Contract | Get Deposit | Start Project |  | compte implementation
2 | RA 2 | 170000 | 70% | 119000 | Write RFP | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Write RFP 7 Get Vendor | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
3 | Omni | 200000 | 35% | 70000 | Write RFP | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Write RFP & Get Vendor | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
4 | AI Use cases | 250000 | 50% | 125000 | Write RFP |  |  |  | Write RFP & Get Vendor | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
5 | Stores / Stock Management | 60000 | 30% | 18000 | Write RFP |  |  |  | Write RFP & Get Vendor | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
6 | Digital Service Centre | 120000 | 40% | 48000 | Write RFP |  |  |  | Write RFP & Get Vendor | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
7 | AFC CBS | 19500 | 65% | 12675 | Win contract | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Win contract | Secure stakeholder 1 | Secure stakeholder 2 | Win tender
8 | AFC Implementation | 39000 | 85% | 33150 | Sign contract | Start project | Clear Governance |  | Sign contract | Start project | Get References
9 | ZB | 140000 | 70% | 98000 | RFP Issued | Secure Partner | Secure stakeholder 1 | Secure stakeholder 2 | RFP Issued | Secure Partner | Secure stakeholder 1 | Secure stakeholder 2
10 | Attie | 145000 | 100% | 145000 | Get Paid balance | Become Current |  |  | Get Paid balance | Become Current
11 | SECZIM - website | 2600 | 100% | 2600 | Get Award | Sign Contract |  |  | Get Award | Sign Contract
12 | Zim Media Commision Digital Transformation | 15000 | 100% | 15000 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3
13 | NRZPF Digitalisation | 15000 | 100% | 15000 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3
14 | SECZIM Digitalisation | 20000 | 100% | 20000 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 | Submit proposal | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3
15 | Bizas rp | 15000 | 50% | 7500 | engage |  |  |  | engage
16 | UX | 20000 | 30% | 6000
17 | Other | 170000 | 70% | 119000 |  | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3 |  | Secure stakeholder 1 | Secure stakeholder 2 | Secure stakeholder 3
|  | 1496300 |  | 930085
Easy Mobile
| Starlink Commision | 13750 | 100% | 13750 | Get License | Secure key Vendors | Sign contrcat | Strategic Plan | Get License | Secure key Vendors | Sign contrcat | Strategic Plan
| Microfinance | 2500 | 100% | 2500 | Apply for License |  |  |  | Apply for License
|  | 16250 |  | 16250
SS Income
| Hotel | 192000 | 100% | 192000 | Start Construction | Buy Cement | Buy Window Frames | Buy Door frames | Start Construction | Finish Roof | Finish Walls | Finish Deck
| Cattle | 9000 | 100% | 9000 | Grow grass - 2 ha | Grow maize - 5ha | Push 8 to heat | Look for bull | Grow grass - 2 ha | Security & Manure | Insermination x 8 | Pay Deposit for Bull
| InDrive | 12480 | 100% | 12480 |  |  |  |  | Get a loan USD7000 | Raise USD3000 | Buy 2 Cars | Register InDrive
|  | 201000 |  | 213480
| Total | 2335350 |  | 1562475
| Balance |  |  | 1562475
| Actual Total Progress | 4.076% |  | 8.596%
| Target progress |  |  | 16.67%
| Gap |  |  | -8.071%
-48.42%

## Foundational
| January |  |  |  | March
Aiia
1. Governance | Board meeting | Board Fees | Get Patron | Revise Constitution | Board meeting | Board Fees | Get Patron | Revise Constitution
2. HR Capacity | Recruit 3 top Notch | Stable/Solid Team |  | Data to staff | Recruit 3 top Notch | Stable/Solid Team | Team Loans | Data to staff
3. Brand | Office Branding | Newspaper articles |  |  | Office Furniture | Newspaper articles
4. Digital 100% Growth | Daily Adverts | WhatsApp to 1000 | Arthur adverts |  | Daily Adverts | WhatsApp to 1000 | Audiances - 1Mllion | Members 300
5. Training | Recruit 3 top Trainers |  |  |  | Recruit 3 top Trainers | Training Content x 10
rubiem
1. Innovations | Kill the entity -legally | email lawyer |  |  | Kill the entity -legally | redo website | register digital sites
2. Build New rubiem | Register new | NSSA for Financials |  |  | PRAZ Registration | NSSA for Financials | ZIMRA Tax clearance
3. NewCo | Register new |  |  |  | Register new | sign agreement
SS Income
1. Farm Capacity | Recruit Stable Worker | Fence fields |  | Repair Kraal | Recruit Stable Worker | camera security | solar fence security | Repair Kraal
2. Farm Mechanisation | Fix Tractor | Borehole Piping. | drip irrigation |  | Fix Tractor |  | drip irrigation
3. Cattle Feed |  |  |  |  | Plant Juncao | Secure Water | Manure/Fertiliser | Sprouting
4. Farm House | Approve design | complete budget |  |  | Approve design | Complete budget | Install Solar System | Complete Temp House
DM
1. PhD | UZ Registration | Proposal Approved |  | Paper 1 draft | UZ Registration | Proposal Approved | write 2 chapters
2. Book | Conclude Theme | Draft concept |  | Draft Contents Table | write 20 chapters | Identify publishers |  | Draft Contents Table
3. SS Closure | Fund Laboratory | Enquire Status |  | Initiate Book | Fund Laboratory | Enquire Status |  | Initiate Book
4. Happiness and love | Share resolutions | AM plan |  | G plan | Implement resolutions | AM plan |  | G plan implementation
5. Network | Cde Simbi | John II |  | VP | CEO + Association | John II | Ministers x 2 | VP