## Plan
ID | Task | Owner | Start | End | Duration (days) | Dependencies | Acceptance / Definition of Done | Artifacts / Outputs | Milestone | Task Explanation
S0 | Project kickoff: scope lock, team roles, cadence, Definition of Done, risk register | Shared | 2026-02-18 | 2026-02-19 | 2 |  | Team norms agreed; repo ready; baseline docs created. | Project charter; DoD; cadence; risk register. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Project kickoff: scope lock, team roles, cadence, Definition of Done, risk register. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
S0.1 | Repo + branching + code review rules + issue templates (bugs/features) | Shared | 2026-02-18 | 2026-02-21 | 4 | S0 | Team norms agreed; repo ready; baseline docs created. | Project charter; DoD; cadence; risk register. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Repo + branching + code review rules + issue templates (bugs/features). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
S0.2 | CI/CD baseline: lint/unit tests/build pipeline, env templates, container skeleton | Shared | 2026-02-20 | 2026-02-26 | 7 | S0.1 | Team norms agreed; repo ready; baseline docs created. | Project charter; DoD; cadence; risk register. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: CI/CD baseline: lint/unit tests/build pipeline, env templates, container skeleton. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
S0.3 | Security baseline: secrets handling policy, audit redaction rules, least-privilege connector plan | Shared | 2026-02-20 | 2026-02-26 | 7 | S0.1 | Team norms agreed; repo ready; baseline docs created. | Project charter; DoD; cadence; risk register. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Security baseline: secrets handling policy, audit redaction rules, least-privilege connector plan. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
INF1 | Provision DEV + UAT environments (network, TLS, DNS) | Shared | 2026-02-20 | 2026-02-27 | 8 | S0.2 | Service deployed; healthcheck OK; documented configuration; backup/restore verified where applicable. | Deployment manifests; runbook; monitoring dashboard link. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Provision DEV + UAT environments (network, TLS, DNS). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
INF2 | Deploy Postgres + backups + restore test (DEV/UAT) | Shared | 2026-02-22 | 2026-03-01 | 8 | INF1 | Service deployed; healthcheck OK; documented configuration; backup/restore verified where applicable. | Deployment manifests; runbook; monitoring dashboard link. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Deploy Postgres + backups + restore test (DEV/UAT). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
INF3 | Deploy Object Storage (S3 compatible) + bucket policies | Shared | 2026-02-22 | 2026-03-01 | 8 | INF1 | Service deployed; healthcheck OK; documented configuration; backup/restore verified where applicable. | Deployment manifests; runbook; monitoring dashboard link. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Deploy Object Storage (S3 compatible) + bucket policies. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
INF4 | Deploy n8n in queue mode + Redis + base credentials structure | Arthur | 2026-02-22 | 2026-03-03 | 10 | INF1 | Service deployed; healthcheck OK; documented configuration; backup/restore verified where applicable. | Deployment manifests; runbook; monitoring dashboard link. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Deploy n8n in queue mode + Redis + base credentials structure. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
INF5 | Observability baseline (structured logs, metrics endpoint, dashboards scaffold) | Shared | 2026-02-25 | 2026-03-06 | 10 | INF1 | Service deployed; healthcheck OK; documented configuration; backup/restore verified where applicable. | Deployment manifests; runbook; monitoring dashboard link. | M1 – Infrastructure & Foundation Ready | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Observability baseline (structured logs, metrics endpoint, dashboards scaffold). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE1 | Backend skeleton (API framework, auth middleware, workspace context) | Shared | 2026-02-25 | 2026-03-06 | 10 | S0.2 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Backend skeleton (API framework, auth middleware, workspace context). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE2 | RBAC model + permissions matrix (admin/member/approver/viewer) | Shared | 2026-03-02 | 2026-03-10 | 9 | BE1 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: RBAC model + permissions matrix (admin/member/approver/viewer). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE3 | Core data model + migrations: workspaces/users/roles/tasks/templates/runs/approvals/audit | Shared | 2026-03-02 | 2026-03-14 | 13 | BE1, INF2 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Core data model + migrations: workspaces/users/roles/tasks/templates/runs/approvals/audit. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE4 | Attachment service: upload/download, virus-scan hook placeholder, SHA256 hashing | Shared | 2026-03-05 | 2026-03-17 | 13 | BE3, INF3 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Attachment service: upload/download, virus-scan hook placeholder, SHA256 hashing. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE5 | Audit engine: event writer, redaction rules, correlation IDs (workspace/task/run) | Shared | 2026-03-05 | 2026-03-17 | 13 | BE3, S0.3 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Audit engine: event writer, redaction rules, correlation IDs (workspace/task/run). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE6 | Task state machine + API (create/list/detail/cancel) | Shared | 2026-03-08 | 2026-03-21 | 14 | BE3 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Task state machine + API (create/list/detail/cancel). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE7 | Template registry + versioning APIs + activate/rollback | Shared | 2026-03-12 | 2026-03-26 | 15 | BE3, BE6 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template registry + versioning APIs + activate/rollback. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
UI1 | UI foundation: design system, navigation, auth screens, workspace switch | Anesu | 2026-03-02 | 2026-03-14 | 13 | BE1 | UI implemented; connects to API; handles empty/error states; meets core UX flow; reviewed in demo. | UI screens; component library updates; UX notes. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: UI foundation: design system, navigation, auth screens, workspace switch. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
UI2 | Task Inbox + Task Detail UI (status timeline, attachments, outputs) | Anesu | 2026-03-08 | 2026-03-24 | 17 | UI1, BE6 | UI implemented; connects to API; handles empty/error states; meets core UX flow; reviewed in demo. | UI screens; component library updates; UX notes. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Task Inbox + Task Detail UI (status timeline, attachments, outputs). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
UI3 | Template Library UI (list/detail/version activation) | Anesu | 2026-03-15 | 2026-03-31 | 17 | UI1, BE7 | UI implemented; connects to API; handles empty/error states; meets core UX flow; reviewed in demo. | UI screens; component library updates; UX notes. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template Library UI (list/detail/version activation). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
UI4 | Approvals UI (queue, approve/reject, evidence preview) | Anesu | 2026-03-22 | 2026-04-07 | 17 | UI2, BE10 | UI implemented; connects to API; handles empty/error states; meets core UX flow; reviewed in demo. | UI screens; component library updates; UX notes. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Approvals UI (queue, approve/reject, evidence preview). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
AI1 | HF model selection + evaluation set (domain tasks, edge cases) | Godswill | 2026-03-02 | 2026-03-10 | 9 | INF1 | Model integrated; JSON-only outputs; schema validation; confidence threshold; logged hash for audit. | Model config; evaluation set; prompt/JSON schema; latency metrics. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: HF model selection + evaluation set (domain tasks, edge cases). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
AI2 | AI Gateway service: classify → extract JSON → validate schema → return confidence | Godswill | 2026-03-08 | 2026-03-21 | 14 | AI1, BE7 | Model integrated; JSON-only outputs; schema validation; confidence threshold; logged hash for audit. | Model config; evaluation set; prompt/JSON schema; latency metrics. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI Gateway service: classify → extract JSON → validate schema → return confidence. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
AI3 | Low-confidence flow: top-3 templates + missing fields generator | Godswill | 2026-03-18 | 2026-03-28 | 11 | AI2, UI2 | Model integrated; JSON-only outputs; schema validation; confidence threshold; logged hash for audit. | Model config; evaluation set; prompt/JSON schema; latency metrics. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Low-confidence flow: top-3 templates + missing fields generator. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
AI4 | Attachment summarization pipeline (optional): summarize + action items + citations pointers | Godswill | 2026-03-22 | 2026-04-04 | 14 | AI2, BE4 | Model integrated; JSON-only outputs; schema validation; confidence threshold; logged hash for audit. | Model config; evaluation set; prompt/JSON schema; latency metrics. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Attachment summarization pipeline (optional): summarize + action items + citations pointers. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE8 | Policy engine v1: approval triggers, allowlists, rate limits, risk flags | Shared | 2026-03-18 | 2026-04-03 | 17 | BE7, S0.3 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Policy engine v1: approval triggers, allowlists, rate limits, risk flags. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE9 | Approval service APIs (request/approve/reject/expire) + audit events | Shared | 2026-03-22 | 2026-04-06 | 16 | BE8, BE5 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Approval service APIs (request/approve/reject/expire) + audit events. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
BE10 | n8n callback endpoints (run-started/completed/failed/approval-request) | Shared | 2026-03-22 | 2026-04-06 | 16 | BE6, INF4 | Endpoint(s) working; unit tests added; RBAC enforced; audit events emitted; tenant scoping verified. | API endpoints; migrations; test report; OpenAPI draft. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: n8n callback endpoints (run-started/completed/failed/approval-request). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
N8N1 | Workflow standards: payload contract, error format, callback usage, idempotency pattern | Arthur | 2026-03-12 | 2026-03-24 | 13 | INF4, BE10 | Standard payload accepted; idempotency enforced; callbacks wired; error format consistent. | Workflow standard doc; sample workflow; payload contract. | M2 – Core Platform Functional | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Workflow standards: payload contract, error format, callback usage, idempotency pattern. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN0 | Finance domain discovery: data sources, constraints, approval matrix | Shared | 2026-03-25 | 2026-04-03 | 10 | BE8 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Finance domain discovery: data sources, constraints, approval matrix. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN1 | Template: Expense Summary Generator (schema + workflow + outputs) | Arthur | 2026-04-01 | 2026-04-14 | 14 | N8N1, FIN0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Expense Summary Generator (schema + workflow + outputs). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN1.AI | AI mapping: expense classification/extraction + receipt summary prompts | Godswill | 2026-04-01 | 2026-04-14 | 14 | AI4, FIN0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: expense classification/extraction + receipt summary prompts. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN2 | Template: Invoice Draft Generator (schema + workflow + outputs) | Arthur | 2026-04-08 | 2026-04-21 | 14 | N8N1, FIN0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Invoice Draft Generator (schema + workflow + outputs). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN2.AI | AI mapping: invoice line items extraction + validation rules | Godswill | 2026-04-08 | 2026-04-21 | 14 | AI2, FIN0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: invoice line items extraction + validation rules. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN3 | Template: Budget Variance Summary (schema + workflow + outputs) | Arthur | 2026-04-15 | 2026-04-28 | 14 | N8N1, FIN0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Budget Variance Summary (schema + workflow + outputs). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
FIN3.AI | AI mapping: variance narrative + KPI extraction from sheets | Godswill | 2026-04-15 | 2026-04-28 | 14 | AI2, FIN0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: variance narrative + KPI extraction from sheets. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS0 | Tech Ops discovery: monitoring/ticketing APIs, severity taxonomy, SLAs | Shared | 2026-04-01 | 2026-04-07 | 7 | BE8 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Tech Ops discovery: monitoring/ticketing APIs, severity taxonomy, SLAs. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS1 | Template: Incident Summary Generator (logs/alerts → summary) | Arthur | 2026-04-06 | 2026-04-18 | 13 | N8N1, OPS0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Incident Summary Generator (logs/alerts → summary). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS1.AI | AI mapping: incident summarization + root-cause hypotheses (flagged) | Godswill | 2026-04-06 | 2026-04-18 | 13 | AI4, OPS0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: incident summarization + root-cause hypotheses (flagged). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS2 | Template: Create Support Ticket (alert → Jira/ServiceNow) | Arthur | 2026-04-10 | 2026-04-22 | 13 | N8N1, OPS0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Create Support Ticket (alert → Jira/ServiceNow). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS2.AI | AI mapping: ticket fields extraction (summary, description, priority, labels) | Godswill | 2026-04-10 | 2026-04-22 | 13 | AI2, OPS0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: ticket fields extraction (summary, description, priority, labels). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS3 | Template: Weekly System Health Report (metrics → report/email) | Arthur | 2026-04-15 | 2026-04-28 | 14 | N8N1, OPS0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Weekly System Health Report (metrics → report/email). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OPS3.AI | AI mapping: health narrative + anomalies detection summary | Godswill | 2026-04-15 | 2026-04-28 | 14 | AI2, OPS0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: health narrative + anomalies detection summary. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM0 | Sales/Marketing discovery: CRM objects, lead fields, compliance for outreach | Shared | 2026-04-08 | 2026-04-14 | 7 | BE8 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Sales/Marketing discovery: CRM objects, lead fields, compliance for outreach. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM1 | Template: Lead Capture → CRM Entry (approval gated) | Arthur | 2026-04-13 | 2026-04-28 | 16 | N8N1, SM0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Lead Capture → CRM Entry (approval gated). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM1.AI | AI mapping: lead extraction from emails/forms + dedupe suggestions | Godswill | 2026-04-13 | 2026-04-28 | 16 | AI2, SM0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: lead extraction from emails/forms + dedupe suggestions. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM2 | Template: Lead Qualification Summary (notes → qualification + next steps) | Arthur | 2026-04-20 | 2026-05-04 | 15 | N8N1, SM0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Lead Qualification Summary (notes → qualification + next steps). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM2.AI | AI mapping: qualification rubric scoring + structured rationale | Godswill | 2026-04-20 | 2026-05-04 | 15 | AI2, SM0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: qualification rubric scoring + structured rationale. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM3 | Template: Campaign Performance Summary (analytics → report) | Arthur | 2026-04-22 | 2026-05-04 | 13 | N8N1, SM0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Campaign Performance Summary (analytics → report). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM3.AI | AI mapping: performance narrative + recommended actions (flagged) | Godswill | 2026-04-22 | 2026-05-04 | 13 | AI2, SM0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: performance narrative + recommended actions (flagged). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM4 | Template: Draft Outreach Email (approval gated) | Arthur | 2026-04-27 | 2026-05-04 | 8 | N8N1, SM0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Draft Outreach Email (approval gated). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
SM4.AI | AI mapping: email draft generator with compliance constraints | Godswill | 2026-04-27 | 2026-05-04 | 8 | AI3, SM0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: email draft generator with compliance constraints. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG0 | Logistics discovery: shipment API, tracking events model, inventory thresholds | Shared | 2026-04-15 | 2026-04-21 | 7 | BE8 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Logistics discovery: shipment API, tracking events model, inventory thresholds. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG1 | Template: Shipment Status Query (tracking → status response) | Arthur | 2026-04-20 | 2026-05-03 | 14 | N8N1, LOG0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Shipment Status Query (tracking → status response). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG1.AI | AI mapping: interpret tracking events into plain-language status | Godswill | 2026-04-20 | 2026-05-03 | 14 | AI2, LOG0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: interpret tracking events into plain-language status. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG2 | Template: Inventory Low-Stock Alert (DB → notify) | Arthur | 2026-04-24 | 2026-05-04 | 11 | N8N1, LOG0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Inventory Low-Stock Alert (DB → notify). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG2.AI | AI mapping: alert explanation + reorder suggestion (flagged) | Godswill | 2026-04-24 | 2026-05-04 | 11 | AI2, LOG0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: alert explanation + reorder suggestion (flagged). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG3 | Template: Delivery Summary Report (deliveries → weekly report) | Arthur | 2026-04-29 | 2026-05-04 | 6 | N8N1, LOG0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Delivery Summary Report (deliveries → weekly report). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG3.AI | AI mapping: delivery exceptions summarization | Godswill | 2026-04-29 | 2026-05-04 | 6 | AI2, LOG0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: delivery exceptions summarization. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG4 | Template: Vendor Communication Draft (approval gated) | Arthur | 2026-05-04 | 2026-05-04 | 1 | N8N1, LOG0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Vendor Communication Draft (approval gated). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
LOG4.AI | AI mapping: vendor email draft with required fields | Godswill | 2026-05-04 | 2026-05-04 | 1 | AI3, LOG0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: vendor email draft with required fields. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV0 | Developer domain discovery: Git provider, CI/CD, permissions model | Shared | 2026-04-15 | 2026-04-21 | 7 | BE8 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Developer domain discovery: Git provider, CI/CD, permissions model. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV1 | Template: Pull Request Summary (PR → summary + risks) | Arthur | 2026-04-22 | 2026-05-04 | 13 | N8N1, DEV0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Pull Request Summary (PR → summary + risks). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV1.AI | AI mapping: PR summarization + change risk flags | Godswill | 2026-04-22 | 2026-05-04 | 13 | AI4, DEV0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: PR summarization + change risk flags. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV2 | Template: Commit Digest Report (commits → digest) | Arthur | 2026-04-27 | 2026-05-04 | 8 | N8N1, DEV0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Commit Digest Report (commits → digest). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV2.AI | AI mapping: digest grouping by component + highlights | Godswill | 2026-04-27 | 2026-05-04 | 8 | AI2, DEV0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: digest grouping by component + highlights. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV3 | Template: Deployment Checklist Generator (release notes → checklist) | Arthur | 2026-05-01 | 2026-05-04 | 4 | N8N1, DEV0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: Deployment Checklist Generator (release notes → checklist). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV3.AI | AI mapping: checklist generation rules + environment-specific steps | Godswill | 2026-05-01 | 2026-05-04 | 4 | AI2, DEV0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: checklist generation rules + environment-specific steps. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV4 | Template: CI/CD Status Report (pipelines → status summary) | Arthur | 2026-05-01 | 2026-05-04 | 4 | N8N1, DEV0 | Template works end-to-end with approval rules; outputs stored as artifacts; audit trail complete. | n8n workflow(s); template schema; sample outputs; demo scenario. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Template: CI/CD Status Report (pipelines → status summary). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
DEV4.AI | AI mapping: failure clustering + suggested next checks (flagged) | Godswill | 2026-05-01 | 2026-05-04 | 4 | AI2, DEV0 | Extraction/drafting outputs match schema; evaluated on sample set; low-confidence handling works. | Prompt templates; extraction schemas; evaluation results. | M3 – Domain Templates Delivered | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: AI mapping: failure clustering + suggested next checks (flagged). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
QA1 | End-to-end test harness for templates (fixtures + replay) | Shared | 2026-04-08 | 2026-04-25 | 18 | BE6, N8N1 | Automated tests running in CI; failures actionable; coverage for critical paths. | Test harness; CI results; load test report. | M4 – Governance & Hardening Complete | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: End-to-end test harness for templates (fixtures + replay). Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
QA2 | Security tests: tenant isolation, RBAC, secrets leakage checks | Shared | 2026-04-22 | 2026-05-04 | 13 | BE2, BE5, BE8 | Automated tests running in CI; failures actionable; coverage for critical paths. | Test harness; CI results; load test report. | M4 – Governance & Hardening Complete | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Security tests: tenant isolation, RBAC, secrets leakage checks. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
QA3 | Performance/load tests: n8n worker scaling, callback throughput | Arthur | 2026-04-29 | 2026-05-04 | 6 | INF4, INF5 | Automated tests running in CI; failures actionable; coverage for critical paths. | Test harness; CI results; load test report. | M4 – Governance & Hardening Complete | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Performance/load tests: n8n worker scaling, callback throughput. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
OBS1 | Operational dashboards: success rate, latency, approvals, AI confidence | Anesu | 2026-04-22 | 2026-05-04 | 13 | INF5, BE5, UI2 | Dashboards/pilot deliverables complete; feedback logged; issues triaged. | Dashboards; pilot report; go/no-go checklist. | M4 – Governance & Hardening Complete | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Operational dashboards: success rate, latency, approvals, AI confidence. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
PIL1 | Pilot onboarding (5–10 users), runbook + support channel | Anesu | 2026-05-01 | 2026-05-04 | 4 | UI2, QA1 | Dashboards/pilot deliverables complete; feedback logged; issues triaged. | Dashboards; pilot report; go/no-go checklist. | M5 – Pilot & Go-Live | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Pilot onboarding (5–10 users), runbook + support channel. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.
PIL2 | Go/No-Go review + executive demo scenario + backlog for Phase 2 | Shared | 2026-05-01 | 2026-05-04 | 4 | PIL1, QA2, QA3 | Dashboards/pilot deliverables complete; feedback logged; issues triaged. | Dashboards; pilot report; go/no-go checklist. | M5 – Pilot & Go-Live | This task delivers a critical component of the Virtual Worker MVP. It supports the AI → Governance → n8n Execution → Audit architecture model. The objective is to complete: Go/No-Go review + executive demo scenario + backlog for Phase 2. Deliverables must comply with the BRS, Conceptual Design, and Technical Design specifications, including RBAC enforcement, template constraints, audit logging, and idempotent execution where applicable.

## Gantt
ID | Task | Owner | W1 18 Feb–24 Feb | W2 25 Feb–03 Mar | W3 04 Mar–10 Mar | W4 11 Mar–17 Mar | W5 18 Mar–24 Mar | W6 25 Mar–31 Mar | W7 01 Apr–07 Apr | W8 08 Apr–14 Apr | W9 15 Apr–21 Apr | W10 22 Apr–28 Apr | W11 29 Apr–05 May
S0 | Project kickoff: scope lock, team roles, cadence, Definition of Done, risk register | Shared | ■
S0.1 | Repo + branching + code review rules + issue templates (bugs/features) | Shared | ■
S0.2 | CI/CD baseline: lint/unit tests/build pipeline, env templates, container skeleton | Shared | ■ | ■
S0.3 | Security baseline: secrets handling policy, audit redaction rules, least-privilege connector plan | Shared | ■ | ■
INF1 | Provision DEV + UAT environments (network, TLS, DNS) | Shared | ■ | ■
INF2 | Deploy Postgres + backups + restore test (DEV/UAT) | Shared | ■ | ■
INF3 | Deploy Object Storage (S3 compatible) + bucket policies | Shared | ■ | ■
INF4 | Deploy n8n in queue mode + Redis + base credentials structure | Arthur | ■ | ■
INF5 | Observability baseline (structured logs, metrics endpoint, dashboards scaffold) | Shared |  | ■ | ■
BE1 | Backend skeleton (API framework, auth middleware, workspace context) | Shared |  | ■ | ■
BE2 | RBAC model + permissions matrix (admin/member/approver/viewer) | Shared |  | ■ | ■
BE3 | Core data model + migrations: workspaces/users/roles/tasks/templates/runs/approvals/audit | Shared |  | ■ | ■ | ■
BE4 | Attachment service: upload/download, virus-scan hook placeholder, SHA256 hashing | Shared |  |  | ■ | ■
BE5 | Audit engine: event writer, redaction rules, correlation IDs (workspace/task/run) | Shared |  |  | ■ | ■
BE6 | Task state machine + API (create/list/detail/cancel) | Shared |  |  | ■ | ■ | ■
BE7 | Template registry + versioning APIs + activate/rollback | Shared |  |  |  | ■ | ■ | ■
UI1 | UI foundation: design system, navigation, auth screens, workspace switch | Anesu |  | ■ | ■ | ■
UI2 | Task Inbox + Task Detail UI (status timeline, attachments, outputs) | Anesu |  |  | ■ | ■ | ■
UI3 | Template Library UI (list/detail/version activation) | Anesu |  |  |  | ■ | ■ | ■
UI4 | Approvals UI (queue, approve/reject, evidence preview) | Anesu |  |  |  |  | ■ | ■ | ■
AI1 | HF model selection + evaluation set (domain tasks, edge cases) | Godswill |  | ■ | ■
AI2 | AI Gateway service: classify → extract JSON → validate schema → return confidence | Godswill |  |  | ■ | ■ | ■
AI3 | Low-confidence flow: top-3 templates + missing fields generator | Godswill |  |  |  |  | ■ | ■
AI4 | Attachment summarization pipeline (optional): summarize + action items + citations pointers | Godswill |  |  |  |  | ■ | ■ | ■
BE8 | Policy engine v1: approval triggers, allowlists, rate limits, risk flags | Shared |  |  |  |  | ■ | ■ | ■
BE9 | Approval service APIs (request/approve/reject/expire) + audit events | Shared |  |  |  |  | ■ | ■ | ■
BE10 | n8n callback endpoints (run-started/completed/failed/approval-request) | Shared |  |  |  |  | ■ | ■ | ■
N8N1 | Workflow standards: payload contract, error format, callback usage, idempotency pattern | Arthur |  |  |  | ■ | ■
FIN0 | Finance domain discovery: data sources, constraints, approval matrix | Shared | [5 empty] | ■ | ■
FIN1 | Template: Expense Summary Generator (schema + workflow + outputs) | Arthur | [6 empty] | ■ | ■
FIN1.AI | AI mapping: expense classification/extraction + receipt summary prompts | Godswill | [6 empty] | ■ | ■
FIN2 | Template: Invoice Draft Generator (schema + workflow + outputs) | Arthur | [7 empty] | ■ | ■
FIN2.AI | AI mapping: invoice line items extraction + validation rules | Godswill | [7 empty] | ■ | ■
FIN3 | Template: Budget Variance Summary (schema + workflow + outputs) | Arthur | [8 empty] | ■ | ■
FIN3.AI | AI mapping: variance narrative + KPI extraction from sheets | Godswill | [8 empty] | ■ | ■
OPS0 | Tech Ops discovery: monitoring/ticketing APIs, severity taxonomy, SLAs | Shared | [6 empty] | ■
OPS1 | Template: Incident Summary Generator (logs/alerts → summary) | Arthur | [6 empty] | ■ | ■ | ■
OPS1.AI | AI mapping: incident summarization + root-cause hypotheses (flagged) | Godswill | [6 empty] | ■ | ■ | ■
OPS2 | Template: Create Support Ticket (alert → Jira/ServiceNow) | Arthur | [7 empty] | ■ | ■ | ■
OPS2.AI | AI mapping: ticket fields extraction (summary, description, priority, labels) | Godswill | [7 empty] | ■ | ■ | ■
OPS3 | Template: Weekly System Health Report (metrics → report/email) | Arthur | [8 empty] | ■ | ■
OPS3.AI | AI mapping: health narrative + anomalies detection summary | Godswill | [8 empty] | ■ | ■
SM0 | Sales/Marketing discovery: CRM objects, lead fields, compliance for outreach | Shared | [7 empty] | ■
SM1 | Template: Lead Capture → CRM Entry (approval gated) | Arthur | [7 empty] | ■ | ■ | ■
SM1.AI | AI mapping: lead extraction from emails/forms + dedupe suggestions | Godswill | [7 empty] | ■ | ■ | ■
SM2 | Template: Lead Qualification Summary (notes → qualification + next steps) | Arthur | [8 empty] | ■ | ■ | ■
SM2.AI | AI mapping: qualification rubric scoring + structured rationale | Godswill | [8 empty] | ■ | ■ | ■
SM3 | Template: Campaign Performance Summary (analytics → report) | Arthur | [9 empty] | ■ | ■
SM3.AI | AI mapping: performance narrative + recommended actions (flagged) | Godswill | [9 empty] | ■ | ■
SM4 | Template: Draft Outreach Email (approval gated) | Arthur | [9 empty] | ■ | ■
SM4.AI | AI mapping: email draft generator with compliance constraints | Godswill | [9 empty] | ■ | ■
LOG0 | Logistics discovery: shipment API, tracking events model, inventory thresholds | Shared | [8 empty] | ■
LOG1 | Template: Shipment Status Query (tracking → status response) | Arthur | [8 empty] | ■ | ■ | ■
LOG1.AI | AI mapping: interpret tracking events into plain-language status | Godswill | [8 empty] | ■ | ■ | ■
LOG2 | Template: Inventory Low-Stock Alert (DB → notify) | Arthur | [9 empty] | ■ | ■
LOG2.AI | AI mapping: alert explanation + reorder suggestion (flagged) | Godswill | [9 empty] | ■ | ■
LOG3 | Template: Delivery Summary Report (deliveries → weekly report) | Arthur | [10 empty] | ■
LOG3.AI | AI mapping: delivery exceptions summarization | Godswill | [10 empty] | ■
LOG4 | Template: Vendor Communication Draft (approval gated) | Arthur | [10 empty] | ■
LOG4.AI | AI mapping: vendor email draft with required fields | Godswill | [10 empty] | ■
DEV0 | Developer domain discovery: Git provider, CI/CD, permissions model | Shared | [8 empty] | ■
DEV1 | Template: Pull Request Summary (PR → summary + risks) | Arthur | [9 empty] | ■ | ■
DEV1.AI | AI mapping: PR summarization + change risk flags | Godswill | [9 empty] | ■ | ■
DEV2 | Template: Commit Digest Report (commits → digest) | Arthur | [9 empty] | ■ | ■
DEV2.AI | AI mapping: digest grouping by component + highlights | Godswill | [9 empty] | ■ | ■
DEV3 | Template: Deployment Checklist Generator (release notes → checklist) | Arthur | [10 empty] | ■
DEV3.AI | AI mapping: checklist generation rules + environment-specific steps | Godswill | [10 empty] | ■
DEV4 | Template: CI/CD Status Report (pipelines → status summary) | Arthur
DEV4.AI | AI mapping: failure clustering + suggested next checks (flagged) | Godswill
QA1 | End-to-end test harness for templates (fixtures + replay) | Shared | [7 empty] | ■ | ■ | ■
QA2 | Security tests: tenant isolation, RBAC, secrets leakage checks | Shared | [9 empty] | ■ | ■
QA3 | Performance/load tests: n8n worker scaling, callback throughput | Arthur | [10 empty] | ■
OBS1 | Operational dashboards: success rate, latency, approvals, AI confidence | Anesu | [9 empty] | ■ | ■
PIL1 | Pilot onboarding (5–10 users), runbook + support channel | Anesu
PIL2 | Go/No-Go review + executive demo scenario + backlog for Phase 2 | Shared